## Gantt Chart
	SMPM Fourier Transverse				26%

			Sunday, April 30, 2017

										14					15					16					17					18					19					20					21					22					23					24					25					26					27					28
WBS	Task Names	Resource Names	Start	Duration	Finish	% Complete	Calendar days	Days Completed	Days Remaining	Mar-17	Apr-17					May-17					Jun-17					Jul-17
			31-Mar-2017	74	15-Jul-2017	26%	107			31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	01	02	03	04	05	06	07	08	09	10	11	12	13	14	15
	Validator		31-Mar-2017	7	10-Apr-2017	100%	11	10	1
	Derivative Terms
	Curl	[name]	31-Mar-2017	1	31-Mar-2017	100%	1	1	0
	Divergence		01-Apr-2017	1	01-Apr-2017	100%	1	1	0
	Double Curl		02-Apr-2017	1	02-Apr-2017	100%	1	1	0
	Gradient		03-Apr-2017	1	03-Apr-2017	100%	1	1	0
	Laplacian		04-Apr-2017	1	04-Apr-2017	100%	1	1	0
	Linear Operators
	Helmholtz Scalar Dirich		05-Apr-2017	1	05-Apr-2017	100%	1	1	0
	Helmholtz Scalar Neuman		06-Apr-2017	1	06-Apr-2017	100%	1	1	0
	Helmholtz Vector Dirich		07-Apr-2017	1	07-Apr-2017	100%	1	1	0
	Helmholtz Vector Neuman		08-Apr-2017	1	08-Apr-2017	100%	1	1	0
	Poisson with deflation		09-Apr-2017	1	09-Apr-2017	50%	1	0	1
	Skew-Symmetric		10-Apr-2017	1	10-Apr-2017	100%	1	1	0
	Milestone 1: SMPM Validated		14-Apr-2017

	Time Dependence	[name]	15-Apr-2017	6	24-Apr-2017	100%	10	6	0
	Write Test Cases	[name]
	Advection Equation	[name]	15-Apr-2017	2	17-Apr-2017	100%	3	2	0
	Diffusion Equation		16-Apr-2017	2	17-Apr-2017	100%	2	2	0
	Advection/Diffusion Equation		17-Apr-2017	2	18-Apr-2017	100%	2	2	0
	Execute Test Cases	[name]
	Advection Equation	[name]	21-Apr-2017	2	24-Apr-2017	50%	4	1	1
	Diffusion Equation		22-Apr-2017	2	24-Apr-2017	50%	3	1	1
	Advection/Diffusion Equation		23-Apr-2017	2	24-Apr-2017	50%	2	1	1
	Milestone 2: Time Integration Validated		28-Apr-2017

	Linear NS Benchmarks	[name]	29-Apr-2017	7	09-May-2017	0%	11	0	7
	Write Test Cases	[name]
	Linear Mode-1 Wave	[name]	29-Apr-2017	3	02-May-2017	0%	4	0	3
	Execute Test Cases	[name]
	Linear Mode-1 Wave	[name]	04-May-2017	4	09-May-2017	0%	6	0	4
	Milestone 3: Linear NS Validated		09-May-2017

	INSE Benchmark	[name]	13-May-2017	13	01-Jun-2017	0%	20	0	83
	Execute Example	[name]
	3D Lid-Driven Cavity (with noise in the transverse)	[name]	13-May-2017	4	17-May-2017	0%	5	0	4
	3D Lock-Exchange	[name]	20-May-2017	4	24-May-2017	0%	5	0	4
	Breaking ISW on undeformed domain	[name]	27-May-2017	4	01-Jun-2017	0%	6	0	4
	Milestone 4: INSE Benchhmarks Validated		01-Jun-2017

	CMOS Conference	[name]	03-Jun-2017	7	10-Jun-2017	0%	8	0	36

	Project Runs	[name]	11-Jun-2017	24	15-Jul-2017	0%	35	0	18
	Write Routine	[name]
	Window Runs	[name]	11-Jun-2017	4	14-Jun-2017	0%	4	0	4
	Execute Run	[name]
	Breaking ISW on deformed domain	[name]	17-Jun-2017	10	29-Jun-2017	0%	13	0	10
	Milestone 5: Project Run Complete		30-Jun-2017

	Dr. Lien Visit	[name]	26-Jun-2017	4	29-Jun-2017	0%	4	0	2

	Submit Proposal	[name]	15-Jul-2017	0	15-Jul-2017	0%	1	0	1
	Proposal Due	[name]	15-Jul-2017	1	15-Jul-2017	0%	1	0	1

	How To Use
	INSERT LINES:
	Insert the required number of lines: click the line number and drag down
	From the template, copy the required section or just one line
	INPUT DATA:
	WBS: to itemize the WBS copy and past the required level from the template
	Enter a Task and Resource Names
	Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
	Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
	Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
	Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
	In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.

		Holidays
		5/29/17
		7/4/17