## Gantt Chart
| SMPM Fourier Transverse |  |  |  | 26%
2017-04-30
[13 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28
WBS | Task Names | Resource Names | Start | Duration | Finish | % Complete | Calendar days | Days Completed | Days Remaining | 2017-03-31 | 2017-04-01 | [29 empty] | 2017-05-01 | [30 empty] | 2017-06-01 | [29 empty] | 2017-07-01
|  |  | 2017-03-31 | 74 | 2017-07-15 | 26% | 107 | time axis 2017-03-31 to 2017-07-15
| Validator |  | 2017-03-31 | 7 | 2017-04-10 | 100% | 11 | 10 | 1 | bar: 2017-03-31 to 2017-05-11
Derivative Terms
| Curl | [name] | 2017-03-31 | 1 | 2017-03-31 | 100% | 1 | 1 | 0
| Divergence |  | 2017-04-01 | 1 | 2017-04-01 | 100% | 1 | 1 | 0
| Double Curl |  | 2017-04-02 | 1 | 2017-04-02 | 100% | 1 | 1 | 0
| Gradient |  | 2017-04-03 | 1 | 2017-04-03 | 100% | 1 | 1 | 0
| Laplacian |  | 2017-04-04 | 1 | 2017-04-04 | 100% | 1 | 1 | 0
Linear Operators
| Helmholtz Scalar Dirich |  | 2017-04-05 | 1 | 2017-04-05 | 100% | 1 | 1 | 0
| Helmholtz Scalar Neuman |  | 2017-04-06 | 1 | 2017-04-06 | 100% | 1 | 1 | 0
| Helmholtz Vector Dirich |  | 2017-04-07 | 1 | 2017-04-07 | 100% | 1 | 1 | 0
| Helmholtz Vector Neuman |  | 2017-04-08 | 1 | 2017-04-08 | 100% | 1 | 1 | 0
| Poisson with deflation |  | 2017-04-09 | 1 | 2017-04-09 | 50% | 1 | 0 | 1
| Skew-Symmetric |  | 2017-04-10 | 1 | 2017-04-10 | 100% | 1 | 1 | 0
| Milestone 1: SMPM Validated |  | 2017-04-14
| Time Dependence | [name] | 2017-04-15 | 6 | 2017-04-24 | 100% | 10 | 6 | 0 | bar: 2017-03-31 to 2017-05-11
| Write Test Cases | [name]
| Advection Equation | [name] | 2017-04-15 | 2 | 2017-04-17 | 100% | 3 | 2 | 0
| Diffusion Equation |  | 2017-04-16 | 2 | 2017-04-17 | 100% | 2 | 2 | 0
| Advection/Diffusion Equation |  | 2017-04-17 | 2 | 2017-04-18 | 100% | 2 | 2 | 0
| Execute Test Cases | [name]
| Advection Equation | [name] | 2017-04-21 | 2 | 2017-04-24 | 50% | 4 | 1 | 1
| Diffusion Equation |  | 2017-04-22 | 2 | 2017-04-24 | 50% | 3 | 1 | 1
| Advection/Diffusion Equation |  | 2017-04-23 | 2 | 2017-04-24 | 50% | 2 | 1 | 1
| Milestone 2: Time Integration Validated |  | 2017-04-28
| Linear NS Benchmarks | [name] | 2017-04-29 | 7 | 2017-05-09 | 0% | 11 | 0 | 7
| Write Test Cases | [name]
| Linear Mode-1 Wave | [name] | 2017-04-29 | 3 | 2017-05-02 | 0% | 4 | 0 | 3
| Execute Test Cases | [name]
| Linear Mode-1 Wave | [name] | 2017-05-04 | 4 | 2017-05-09 | 0% | 6 | 0 | 4
| Milestone 3: Linear NS Validated |  | 2017-05-12
| INSE Benchmark | [name] | 2017-05-13 | 13 | 2017-06-01 | 0% | 20 | 0 | 83
| Execute Example | [name]
| 3D Lid-Driven Cavity (with noise in the transverse) | [name] | 2017-05-13 | 4 | 2017-05-17 | 0% | 5 | 0 | 4
| 3D Lock-Exchange | [name] | 2017-05-20 | 4 | 2017-05-24 | 0% | 5 | 0 | 4
| Breaking ISW on undeformed domain | [name] | 2017-05-27 | 4 | 2017-06-01 | 0% | 6 | 0 | 4
| Milestone 4: INSE Benchhmarks Validated |  | 2017-06-01
| CMOS Conference | [name] | 2017-06-03 | 7 | 2017-06-10 | 0% | 8 | 0 | 36
| Project Runs | [name] | 2017-06-11 | 24 | 2017-07-15 | 0% | 35 | 0 | 18
| Write Routine | [name]
| Window Runs | [name] | 2017-06-11 | 4 | 2017-06-14 | 0% | 4 | 0 | 4
| Execute Run | [name]
| Breaking ISW on deformed domain | [name] | 2017-06-17 | 10 | 2017-06-29 | 0% | 13 | 0 | 10
| Milestone 5: Project Run Complete |  | 2017-06-30
| Dr. Lien Visit | [name] | 2017-06-26 | 4 | 2017-06-29 | 0% | 4 | 0 | 2
| Submit Proposal | [name] | 2017-07-15 | 0 | 2017-07-15 | 0% | 1 | 0 | 1
| Proposal Due | [name] | 2017-07-15 | 1 | 2017-07-15 | 0% | 1 | 0 | 1
How To Use
INSERT LINES:
Insert the required number of lines: click the line number and drag down
From the template, copy the required section or just one line
INPUT DATA:
WBS: to itemize the WBS copy and past the required level from the template
Enter a Task and Resource Names
Enter a [Start] date and a [Duration] (working days); The Due date is calculated and the task bar shows the task's duration on calendar.
Or: Enter a [Start] and [Due] dates; The [Duration] (working days) is calculated and the task bar shows the task's duration on calendar.
Enter a percentage in the [% Complete box]; the task bar shows a progress bar to indicate what percentage of the task is complete.
Milestone: If you enter a start date without an end date, a milestone marker is displayed on the bar chart.
In Categories tasks (level 1) Start, Due, Duration and Percentage Complete values are calculated; however they can be overwritten.
Holidays
2017-05-29
2017-07-04